Minutes of the Building Committee

GHS Music Instructional Space and Auditorium Project

Date:		June 15, 2010

Location:	Staff Development Room, Havemeyer building

Attendees:	Committee Voting Members – Robert Brady, Leslie Cooper, Leslie Moriarty,   Joe Ross.

Ex-Officio –  Bob Kavee, Peter Robinson, Sid Freund.

Other – Kathy Cowles and Javier Salazar from Perkins + Will, Ty Tregellas and Joe Rossetti from Turner, Bob Lichtenfeld, Jeff Spector, Sue Chipouras, Chris Winters, Pam Speer, Neil Bouknight

The meeting was called to order at 7:35 a.m. by Joe Ross, Chairman.

The Building Committee reported that P&Z granted preliminary site plan approval and municipal improvement status at its June 1st meeting.  The Committee discussed and agreed to hire a land use attorney to assist with the ARC and ZBA processes.

The Building Committee reviewed the current project cost estimates compared to the estimates at the end of schematic design.  The Committee discussed modifications to the project which might lower the current cost; however all require changes to the Ed Specs.  The information will be presented to the Board of Education at its June 24, 2010 meeting.  The following charts present the cost estimate data:

|  | Schematic |  | Design |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Design |  | Development |  |  |
|  | Oct 2009 |  | June 2010 |  | Variance |
| Hard Costs | 22,155,000 |  | 23,078,000 |  | 923,000 |
| Technology/FFE | 1,710,000 |  | 1,960,000 |  | 250,000 |
| Soft Costs | 1,200,000 |  | 1,330,000 |  | 130,000 |
| Contingency | 2,750,000 |  | 2,442,000 |  | (308,000) |
| Cost Escalation | 0 |  | 460,000 |  | 460,000 |
| Total | 27,815,000 |  | 29,270,000 |  | 1,455,000 |

| Key Reasons for Variance: |  |  |  |  |
| --- | --- | --- | --- | --- |
| Site plan changes | 330,000 |  | Increased site elements for Wetlands approval |  |
| Choir Room ceiling height | 320,000 |  | Acoustician recommendation for proper sound quality |  |
| Site Lighting | 235,000 |  | Improved exterior and parking lighting for neighbor |  |
|  |  |  | support and P&Z approval |  |
| Increased hard cost accuracy | 38,000 |  |  |  |
| Subtotal Hard Cost Variance | 923,000 |  |  |  |
| Increased FF&E | 250,000 |  | Better definition of equipment needs |  |
| Soft Costs | 130,000 |  | Better definition of project needs |  |
| Contingency | (308,000) |  | Better definition and accuracy |  |
| Construction cost escalation | 460,000 |  | 3rd qtr 2011 project start versus 3rd qtr 2010 |  |
| Total | 1,455,000 |  |  |  |

| Possible Additions/Deletions |
| --- |
| Choral Room - do not raise ceiling | (320,000) |
| Delete orchestra pit hydraulic lift | (175,000) |
| Reduce FF&E - auditorium equipment (lights, AV) | (150,000) |
| Reduce FF&E - other (computers, furniture) | TBD |
| Lower auditorium height by 2 feet | (93,000) |
| Reduce finishes (interior and exterior) | TBD |
| Other modifications (e.g., square footage) | TBD |
| Add repaving of entire parking lot | 240,000 |
| Other Variables |  |
| Changes from Land Use reviews (ZBA, ARC) | TBD |
| Construction cost escalation (past 3rd qtr 2011) | TBD |

The next regular meeting will be Tuesday, July 6, 2010 at 7:30 a.m. in the Staff Development Room at Havemeyer.  A motion was made and approved to adjourn the meeting at 9:05 a.m.

Respectfully submitted,

Leslie Moriarty					Joe Ross
Clerk							Chairman